ESF Self-Study Timeline (Proposed Draft)
Fall 2019 – Spring 2022

☒ October 28 – 29, 2019: Invitation Only MSCHE Self-Study Institute (John W, Tom C, Sophie G-J)

☒ November 7, 2019: Meet with President David Amberg to build engagement at the 
     executive level for this 2-year process

☒ November 8, 2019: Meet with Academic Council to cover proposed timeline and expectations

☒ November 12, 2019: Academic Governance, campus update

☒  November 14, 2019: Invite AC, EC, and other campus stakeholders to assist with identifying 
      institutional priorities through a Qualtrics survey designed around institutional strategic plan   
      (Standard I – Mission & Goals)

☒ Update https://www.esf.edu/middlestates with current information regarding Self-Study progress, opportunities to provide input, etc.

☐ December 3, 2019: Academic Governance, campus update

☐ December 4, 2019: Conference Call with VP Liaison, Dr. Hilda Colón Plumey

☐ January 21, 2020: Academic Governance, campus update

☐ December 2019: January 2020: Assemble Steering Committee & Work Groups

☐ February 18, 2020: Academic Governance, campus update

☐ By April 1, 2020: Submit draft of Self-Study Design (SSD) to Dr. Plumey, 2 weeks prior to visit

☐ March 2020 – September 2020: Dr. Dr. Hilda Colón Plumey to visit ESF Campus

☐ March 24, 2020: Academic Governance, campus update

☐ April 21, 2020: Academic Governance, campus update

☐ May 7, 2020: Academic Governance, campus update

☐ Summer 2020: Dr. Hilda Colón Plumey will offer revision opportunity and accept SSD

☐ September 2020 – December 2020: Working groups gather and analyze data and submit reports to 
     Steering Committee

☐ January 2021 – May 2021: Team Chair Chosen, Visit Date (March 2022) Chosen, SSD sent to Chair,      
     Self-Study Report drafted and shared with campus community for comment

☐ May 2021 – September 2021: Self-Study Report revisions and campus review/comment period

☐ September 2021 – November 2021: Self-Study Report draft sent to Team Chair for feedback

☐ September 2021 – November 2021: Team Chair Visits (2 weeks after sending SS Report)

☐ December 2021 – January 2022: Self Study Report finalized based on Team Chair’s feedback

☐ February 1, 2022: Self Study Report, Evidence Inventory, Verification of Compliance uploaded to   
     MSCHE Portal (six weeks before scheduled team visit)

☐ March 2022: Full Evaluation Team on campus for review